## Evolution 2
source: | https://docs.google.com/spreadsheets/d/1dzZPqFlh6F6VBjymXkqyMzmmXedSpWSH8u42LtlH678/edit#gid=576357853
Stages | Goal | Task | Estimated Hours | Assigned To | Target Deadline | Actual Hours | Actual Delivery Date | Status | Comment
1 | Project Set Up | Understand Requirement | 3 | Whole Team | 2024-03-28 | 10 | 2024-04-04 | Finished
|  | Software Requirement Specification (SRS) Document (20%) | 5 | Yuyu | 2024-04-11 | 12 | 2024-04-13 | Finished
|  | Use Case mapping | 1 | Yuyu | 2024-04-14 | 1 | 2024-04-14 | Finished
2 | Design UML (30% in total for design) | initial set up | 2 | Whole Team | 2024-04-05 | 2 | 2024-04-05 | Finished
|  | Client | 2 | Haolou | 2024-04-10 | 2 | 2024-04-06 | Finished
|  | Server | 2 | Hunter | 2024-04-11 | 2 | 2024-04-12 | Finished
|  | Admin | 2 | Hiep | 2024-04-14 | 2 | 2024-04-13 | Reviewed & Merged
|  | Course Mangement | 2 | Haolou | 2024-04-13 | 2 | 2024-04-12 | Finished
|  | DAO | 2 | Steven | 2024-04-14 | 2 | 2024-04-15 | Finished
|  | Models | 1 | Steven | 2024-04-14 | 2 | 2024-04-15 | Finished
3 | Change Impact Report | Finish drafting all changes, decision making | 1 | Yuyu | 2024-04-14 | 1 | 2024-04-14 | Finished
|  | Finish changes in data storage and changes in data model | 2 | Steven | 2024-04-14 | 2 | 2024-04-14 | Finished
|  | Finalize the document as a report | 5 | Whole Team | 2024-04-15 | 6 | 2024-04-15 | Finished
4 | Task Breakdown (20%) | Fill names to all responsibilities | 1 | Yuyu | 2024-04-10 | 1 | 2024-04-14 | Finished
|  | Fill all estimated hours | 1 | Hiep | 2024-04-11 | 1 | 2024-04-11 | Finished
|  | Fill all actual hours | 1 | Whole Team | 2024-04-15 | 1 | 2024-04-15 | Finished
|  | Fill status update | 1 | Whole Team | 2024-04-15 | 1 | 2024-04-15 | Finished
|  | Fill all delivery dates | 1 | Whole Team | 2024-04-15 | 1 | 2024-04-15 | Finished
5 | Create GitLab Issues Bases on Tasks |  | 3 | Yuyu | 2024-04-12 | 3 | 2024-04-14 | Finished
6 | CI/CD set up |  | 6 | Hunter | 2024-04-07 | 8 | 2024-04-07 | Finished
7 | Database set up | build up database | 3 | Steven | 2024-04-07 | 3 | 2024-04-07 | Finished
|  | DAO database management - lecture dao | 3 | Steven | 2024-04-07 | 3 | 2024-04-08 | Finished
|  | DAO database management - student dao | 2 | Yuyu | 2024-04-07 | 3 | 2024-04-08 | Finished
|  | DAO database management - professor dao | 2 | Yuyu | 2024-04-07 | 3 | 2024-04-08 | Finished
|  | DAO database management - instructor dao | 1 | Yuyu | 2024-04-07 | 1 | 2024-04-07 | Finished
|  | DAO database management - attedance status dao | 1 | Yuyu | 2024-04-07 | 1 | 2024-04-07 | Finished
|  | DAO database management - attedance record dao | 1 | Yuyu | 2024-04-07 | 1 | 2024-04-07 | Finished
|  | DAO database management - notificaiton preference dao | 1 | Yuyu | 2024-04-07 | 1 | 2024-04-07 | Finished
|  | DAO database management - SectionEnrollment dao | 2 | Steven | 2024-04-07 | 1 | 2024-04-08 | Finished
|  | DAO database management - course dao | 1 | Steven | 2024-04-07 | 3 | 2024-04-08 | Finished
|  | DAO database management - section dao | 2 | Steven | 2024-04-07 | 3 | 2024-04-08 | Finished
8 | Minimum Attendacne Management System | socket communication - front end | 3 | Haolou | 2024-04-10 | 3 | 2024-04-10 | Finished
|  | socket communication - backend | 3 | Hunter | 2024-04-10 | 3 | 2024-04-10 | Finished
|  | modify backend api | 3 | Hunter | 2024-04-11 | 3 | 2024-04-11 | Finished
|  | app skeleton - professor log in - choose one course - take attendance - return one student name | 5 | Haolou | 2024-04-07 | 5 | 2024-04-07 | Finished
|  | Testing a working system | 2 | Whole Team | 2024-04-15 | 2 | 2024-04-15 | Finished
9 | Admin functions: | super user dao | 1 | Yuyu | 2024-04-13 | 1 | 2024-04-13 | Finished
|  | super user sign in | 1 | Hiep | 2024-04-13 | 2 | 2024-04-13 | Finished
|  | Functional Setup | 2 | Hiep | 2024-04-12 | 3 | 2024-04-12 | Finished
|  | Add new users (manually, by batch from a file) | 2 | Hiep | 2024-04-14 | 3 | 2024-04-14 | Finished
|  | password encryption | 3 | Yuyu | 2024-04-14 | 2 | 2024-04-14 | Finished
|  | modify information of a user | 2 | Hiep | 2024-04-14 | 2 | 2024-04-12 | Finished
10 | Course Mangement | super user log in | 1 | Haolou | 2024-04-12 | 1 | 2024-04-12 | Finished
|  | Functional Setup | 2 | Haolou | 2024-04-12 | 2 | 2024-04-12 | Finished
|  | Create a new course/ with section/ session (manual) | 1 | Haolou | 2024-04-12 | 1 | 2024-04-12 | Finished
|  | Create a new course/ with section/ session (batch) | 2 | Hunter | 2024-04-13 | 3 | 2024-04-13 | Finished
|  | Add a new session for a existing course | 1 | Haolou | 2024-04-12 | 1 | 2024-04-12 | Finished
|  | modify a course/session | 1 | Haolou | 2024-04-12 | 2 | 2024-04-12 | Finished
|  | delete a course/session (with confirmation message) | 1 | Haolou | 2024-04-12 | 2 | 2024-04-12 | Finished
|  | Enroll a student manually | 2 | Haolou | 2024-04-12 | 2 | 2024-04-12 | Finished
|  | modify student enrollment | 1 | Haolou | 2024-04-12 | 1 | 2024-04-12 | Finished
11 | Faculty functions | take attendance (able to specify time) | 2 | Hunter | 2024-04-12 | 2 | 2024-04-12 | Finished
|  | modify previously taken record | 1 | Hunter | 2024-04-12 | 2 | 2024-04-12 | Finished
|  | generate attendance report | 1 | Hunter | 2024-04-12 | 2 | 2024-04-12 | Finished
12 | Student functions: | change notification perference | 1 | Hunter | 2024-04-12 | 1 | 2024-04-12 | Finished
|  | get summary and detailed reoprt | 1 | Hunter | 2024-04-12 | 2 | 2024-04-12 | Finished
13 | Send report / notification | weekly report email | 1 | Hunter |  | 1 |  | Finished
|  | generate notification when attendance status change (based on the preference) | 1 | Hunter | 2024-04-11 | 1 | 2024-04-11 | Finished
14 | Test Coverage | Client | 4 | Haolou | 2024-04-16 | 5 | 2024-04-16 | Finished
|  | Server | 4 | Hunter | 2024-04-12 | 5 | 2024-04-16 | Finished
|  | Course Management | 2 | Haolou | 2024-04-16 | 4 | 2024-04-16 | Finished
|  | Admin | 2 | Hiep | 2024-04-15 | 4 | 2024-04-15 | Finished
|  | DAO | 3 | Steven | 2024-04-14 | 4 | 2024-04-16 | Finished
Total |  |  | 125 |  |  | 162

## Evolution 3
source | https://docs.google.com/spreadsheets/d/1dzZPqFlh6F6VBjymXkqyMzmmXedSpWSH8u42LtlH678/edit#gid=1390923432
Stages | Goal | Task | Estimated Hours | Assigned To | Target Deadline | Actual Hours | Actual Delivery Date | Status | Comment
1 | Project Set Up | Understand Requirement | 1 | Yuyu | 2024-04-20 | 1 | 2024-04-20 | Finished
|  | Software Requirement Specification (SRS) | 3 | Steven | 2024-04-27 | 4 | 2024-04-27 | Finished
2 | Design UML update | Client | 2 | Steven | 2024-04-29 | 2 | 2024-04-30 | Finished
|  | Admin | 1 | Hiep | 2024-04-29 | 1 | 2024-04-30 | Finished
|  | Course Mangement | 1 | Hiep | 2024-04-29 | 1 | 2024-04-30 | Finished
3 | Change Impact Report | Client | 1 | Haolou | 2024-04-30 | 1 | 2024-05-01 | Finished
|  | Admin | 1 | Hiep | 2024-04-30 | 1 | 2024-05-01 | Finished
|  | Course Mangement | 1 | Hiep | 2024-04-30 | 1 | 2024-05-01 | Finished
4 | Task Breakdown (20%) | Fill names to all responsibilities | 1 | Yuyu | 2024-04-20 | 1 | 2024-04-20 | Finished
|  | Fill all estimated hours | 1 | Yuyu | 2024-04-20 | 1 | 2024-04-21 | Finished
|  | Fill all actual hours | 1 | Whole Team | 2024-04-30 | 1 | 2024-05-01 | Finished
|  | Fill status update | 1 | Whole Team | 2024-04-30 | 1 | 2024-05-01 | Finished
5 | Tasks tracking | Create GitLab Issues | 1 | Yuyu | 2024-04-22 | 1 | 2024-04-23 | Finished
6 | Attendance taking app GUI | Basic GUI set up | 5 | Hunter | 2024-04-25 | 6 | 2024-04-26 | Finished
|  | attendance taking | 3 | Hunter | 2024-04-26 | 2 | 2024-04-26 | Finished
|  | modify attendance | 3 | Hunter | 2024-04-26 | 1 | 2024-04-26 | Finished
|  | generate report function | 4 | Haolou | 2024-04-27 | 3 | 2024-04-26 | Finished
|  | student view | 4 | Haolou | 2024-04-28 | 6 | 2024-04-29 | Finished
|  | UI improvement | 3 | Haolou | 2024-04-29 | 2 | 2024-04-29 | Finished
|  | docker set up | 3 | Hunter | 2024-04-20 | 2 | 2024-04-30 | Finished
7 | FX application - admin/course management | Set up package dependencies | 5 | Hiep | 2024-04-22 | 8 | 2024-04-24 | Finished
|  | Structures for Admin | 3 | Hiep | 2024-04-23 | 3 | 2024-04-25 | Finished
|  | Structure for CourseMangement | 3 | Hiep | 2024-04-23 | 4 | 2024-04-25 | Finished
|  | File input | 2 | Hiep | 2024-04-25 | 1 | 2024-04-26 | Finished
|  | Alertbox | 1 | Hiep | 2024-04-26 | 1 | 2024-04-26 | Finished
|  | ConfirmBox | 1 | Hiep | 2024-04-26 | 1 | 2024-04-26 | Finished
|  | ListView | 2 | Hiep | 2024-04-27 | 1 | 2024-04-26 | Finished
|  | CourseMangement Section options | 2 | Hiep | 2024-04-28 | 3 | 2024-04-27 | Finished
|  | CourseMangement Lecture Input | 1 | Hiep | 2024-04-29 | 1 | 2024-04-28 | Finished
|  | Admin App testing | 4 | Haolou | 2024-04-28 | 5 | 2024-04-27 | Finished
|  | Course Mangement App testing | 5 | Haolou | 2024-04-29 | 4 | 2024-04-28 | Finished
|  | Css Configuration | 2 | Hiep | 2024-04-27 | 2 | 2024-04-27 | Finished
8 | installation and configuration instructions | FX application | 2 | Hiep | 2024-04-30 | 3 | 2024-04-30 | Finished
|  | Attendance management app | 1 | Hunter | 2024-04-30 | 1 | 2024-05-01 | Finished
9 | extra credit | QR code functionality | 4 | Steven | 2024-04-29 | 5 | 2024-04-29 | Finished
|  | GPS location checking | 4 | Hunter | 2024-04-30 | 6 | 2024-04-29 | Finished
|  | EC defense presentation | 2 | Hunter | 2024-04-30 | 3 | 2024-04-30 | Finished
|  | integrate to Attenfacne taking app | 2 | Hunter | 2024-04-30 | 2 | 2024-04-29 | Finished
Total |  |  | 87 |  |  | 93