## Evolution 3
source | https://docs.google.com/spreadsheets/d/1dzZPqFlh6F6VBjymXkqyMzmmXedSpWSH8u42LtlH678/edit#gid=1390923432
Stages | Goal | Task | Estimated Hours | Assigned To | Target Deadline | Actual Hours | Actual Delivery Date | Status | Comment
1 | Project Set Up | Understand Requirement | 1 | Yuyu | 2024-04-20 | 1 | 2024-04-20 | Finished
|  | Software Requirement Specification (SRS) | 3 | Steven | 2024-04-27 | 4 | 2024-04-27 | Finished
2 | Design UML update | Client | 2 | Steven | 2024-04-29 | 2 | 2024-04-30 | Finished
|  | Admin | 1 | Hiep | 2024-04-29 | 1 | 2024-04-30 | Finished
|  | Course Mangement | 1 | Hiep | 2024-04-29 | 1 | 2024-04-30 | Finished
3 | Change Impact Report | Client | 1 | Haolou | 2024-04-30 | 1 | 2024-05-01 | Finished
|  | Admin | 1 | Hiep | 2024-04-30 | 1 | 2024-05-01 | Finished
|  | Course Mangement | 1 | Hiep | 2024-04-30 | 1 | 2024-05-01 | Finished
4 | Task Breakdown (20%) | Fill names to all responsibilities | 1 | Yuyu | 2024-04-20 | 1 | 2024-04-20 | Finished
|  | Fill all estimated hours | 1 | Yuyu | 2024-04-20 | 1 | 2024-04-21 | Finished
|  | Fill all actual hours | 1 | Whole Team | 2024-04-30 | 1 | 2024-05-01 | Finished
|  | Fill status update | 1 | Whole Team | 2024-04-30 | 1 | 2024-05-01 | Finished
5 | Tasks tracking | Create GitLab Issues | 1 | Yuyu | 2024-04-22 | 1 | 2024-04-23 | Finished
6 | Attendance taking app GUI | Basic GUI set up | 5 | Hunter | 2024-04-25 | 6 | 2024-04-26 | Reviewed & Merged
|  | attendance taking | 3 | Hunter | 2024-04-26 | 2 | 2024-04-26 | Reviewed & Merged
|  | modify attendance | 3 | Hunter | 2024-04-26 | 1 | 2024-04-26 | Reviewed & Merged
|  | generate report function | 4 | Haolou | 2024-04-27 | 3 | 2024-04-26 | Reviewed & Merged
|  | student view | 4 | Haolou | 2024-04-28 | 6 | 2024-04-29 | Reviewed & Merged
|  | UI improvement | 3 | Haolou | 2024-04-29 | 2 | 2024-04-29 | Reviewed & Merged
|  | docker set up | 3 | Hunter | 2024-04-20 | 2 | 2024-04-30 | Reviewed & Merged
7 | FX application - admin/course management | Set up package dependencies | 5 | Hiep | 2024-04-22 | 8 | 2024-04-24 | Reviewed & Merged
|  | Structures for Admin | 3 | Hiep | 2024-04-23 | 3 | 2024-04-25 | Reviewed & Merged
|  | Structure for CourseMangement | 3 | Hiep | 2024-04-23 | 4 | 2024-04-25 | Reviewed & Merged
|  | File input | 2 | Hiep | 2024-04-25 | 1 | 2024-04-26 | Reviewed & Merged
|  | Alertbox | 1 | Hiep | 2024-04-26 | 1 | 2024-04-26 | Reviewed & Merged
|  | ConfirmBox | 1 | Hiep | 2024-04-26 | 1 | 2024-04-26 | Reviewed & Merged
|  | ListView | 2 | Hiep | 2024-04-27 | 1 | 2024-04-26 | Reviewed & Merged
|  | Css Conf | 2 | Hiep | 2024-04-27 | 2 | 2024-04-27 | Reviewed & Merged
8 | installation and configuration instructions | FX application | 2 | Hiep | 2024-04-30 | 3 | 2024-04-30 | Reviewed & Merged
|  | Attendance management app | 1 | Hunter | 2024-04-30 | 1 | 2024-05-01 | Reviewed & Merged
9 | extra credit | QR code functionality | 4 | Steven | 2024-04-29 | 5 | 2024-04-29 | Reviewed & Merged
|  | GPS location checking | 4 | Hunter | 2024-04-30 | 6 | 2024-04-29 | Reviewed & Merged
|  | integrate to Attenfacne taking app | 2 | Hunter | 2024-04-30 | 2 | 2024-04-29 | Reviewed & Merged